## Overview
CRMfic - Full Application QA Test Plan
Module | Test Cases
Auth & Account | 9
Contacts | 9
Lists & Tags | 4
Campaigns (Email) | 10
Recurring Email | 5
Sequences | 8
Automation | 6
Sending & SMTP | 4
Webhooks | 3
Media, Settings & Global | 5
Cross-Cutting | 4
TOTAL | 67
How to use: fill in Status (dropdown: Not Tested / Pass / Fail / Blocked) and Notes / Bug Ref per row on each module tab.

## Auth & Account
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
AUTH-001 | Register | New user sign-up | 1. Go to Register 2. Fill name/email/password 3. Submit | Account created; verification email (link + 6-digit OTP) sent; redirected to verify-email notice.
AUTH-002 | Register | Email verification - link | 1. Open verification email 2. Click the signed link | Email marked verified; user redirected into the app.
AUTH-003 | Register | Email verification - OTP | 1. On verify-email screen, enter the 6-digit code from the email | Email marked verified without needing the link.
AUTH-004 | Login | Login with valid credentials | 1. Go to Login 2. Enter correct email/password 3. Submit | Redirected to Dashboard/Home.
AUTH-005 | Login | Login with invalid credentials | 1. Enter wrong password 2. Submit | Inline error shown, not logged in.
AUTH-006 | Password | Forgot / reset password | 1. Click 'Forgot password' 2. Submit email 3. Open reset link from email 4. Set new password | Password updated; can log in with the new password.
AUTH-007 | Two-Factor | Enable 2FA | 1. Go to Settings/Profile 2. Enable Two-Factor Authentication 3. Scan QR & confirm code | 2FA enabled; next login prompts for an authenticator code.
AUTH-008 | Two-Factor | Login with 2FA challenge | 1. Log out 2. Log back in with correct password 3. Enter 2FA code | Access granted only after a correct 2FA code.
AUTH-009 | Session | Logout | 1. Click the logout icon (top right) | Session ends; redirected to Login; back button doesn't restore access.

## Contacts
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
CONT-001 | List | View & search contacts | 1. Go to Contacts 2. Use search box / status filter | List narrows to matching contacts; pagination works.
CONT-002 | Create/Edit | Add a contact manually | 1. Click Add Contact 2. Fill required fields 3. Save | New contact appears in the list and is openable.
CONT-003 | Create/Edit | Edit contact detail | 1. Open a contact 2. Edit fields (name, email, timezone) 3. Save | Changes persist after reload.
CONT-004 | Detail | Attach/detach list & tag | 1. On contact detail, add a List and a Tag 2. Remove one of each | List/Tag membership updates immediately and is reflected on the Lists/Tags pages.
CONT-005 | Detail | Add / delete a note | 1. On contact detail, add a note 2. Delete it | Note appears in the activity/notes panel, then is removed.
CONT-006 | Detail | Activity timeline | 1. Trigger an action for a contact (e.g. add to a list, send a campaign) | A corresponding entry appears in the contact's activity log.
CONT-007 | Bulk | Import contacts (CSV) | 1. Contacts > Import 2. Upload a CSV, map columns 3. Confirm import | Contacts are created/updated in bulk; import summary shows counts (created/skipped/errors).
CONT-008 | Bulk | Export contacts | 1. Contacts > Export (optionally with filters applied) | A CSV downloads containing the filtered contact set.
CONT-009 | Bulk | Delete contact(s) | 1. Select one or more contacts 2. Delete, confirm | Contact(s) removed from the list.

## Lists & Tags
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
LIST-001 | Lists | Create / rename / delete a list | 1. Go to Lists 2. Create new list 3. Rename it 4. Delete it | List CRUD works; contact counts shown are accurate.
LIST-002 | Lists | View contacts in a list | 1. Open a list | Shows only contacts belonging to that list.
LIST-003 | Tags | Create / rename / delete a tag | 1. Go to Tags 2. Create new tag 3. Rename it 4. Delete it | Tag CRUD works; usage counts shown are accurate.
LIST-004 | Tags | Apply a tag from Contacts | 1. On a contact, apply an existing tag or create one inline | Tag appears on the contact and the Tags page count increments.

## Campaigns (Email)
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
CMP-001 | Create | Compose a campaign | 1. Campaigns > Create campaign 2. Set subject/pre-header 3. Build email body in editor | Draft saves automatically; body renders correctly in Preview.
CMP-002 | Create | Upload image/video in editor | 1. In the email editor, insert an image/video block 2. Upload a file | Media uploads, appears in the block, and is retrievable later (media library).
CMP-003 | Recipients | List & Tag targeting | 1. In Recipients step, add included/excluded list+tag rows | Live recipient count updates to match the selection.
CMP-004 | Recipients | Advanced Filter targeting | 1. Switch to Advanced Filter 2. Build a condition (e.g. 'opened campaign X') 3. Apply | Recipient count reflects the filter; invalid filters show a clear error instead of silently returning 0.
CMP-005 | Send | Send now | 1. Review step 2. Choose 'Send now' 3. Confirm | Campaign status moves to Sending/Sent; recipients receive the email (check Mailpit/inbox).
CMP-006 | Send | Schedule for later | 1. Choose 'Schedule' 2. Pick a future date/time 3. Confirm | Campaign shows Scheduled and does not send before the chosen time.
CMP-007 | Send | Send within a date range | 1. Choose 'Range' 2. Pick start/end 3. Confirm | Emails are spread across the range rather than all firing at once.
CMP-008 | Post-send | Send a test email | 1. From the editor, click Send Test 2. Enter an address | Test email arrives with correct subject/body/sender.
CMP-009 | Post-send | View report | 1. Open a sent campaign's Report | Shows delivered/opens/clicks/unsubscribes/bounces with a working per-tab contact list.
CMP-010 | Manage | Duplicate / delete campaign | 1. From Campaigns list, duplicate a campaign 2. Delete the original | Duplicate opens as a new Draft with the same content; delete removes the original.

## Recurring Email
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
REC-001 | Create | Create a recurring email | 1. Recurring Email > Create 2. Set frequency (daily/weekly/monthly) + time 3. Compose content 4. Set recipients | Template saves as Draft with next-run date computed correctly for the chosen frequency.
REC-002 | Activate | Activate / pause | 1. Toggle status to Active 2. Toggle to Paused | Active: next_run_at is set and it fires on schedule. Paused: no further occurrences fire.
REC-003 | Occurrence | Occurrence fires on schedule | 1. Set a near-future time 2. Wait for the scheduled cron tick | A new occurrence is created & sent automatically; 'Last Sent' and 'Sent This Month' stats update.
REC-004 | Occurrence | Email History per occurrence | 1. Open a recurring email's Email History tab 2. Open an occurrence's report | Each occurrence lists its own recipients/sent/opens/clicks; report drills into that occurrence only.
REC-005 | Occurrence | Preview & send test | 1. From an occurrence row's (...) menu, Preview Email / send a test | Preview renders the snapshot content sent at that time; test email arrives correctly.

## Sequences
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
SEQ-001 | Builder | Create sequence & add steps | 1. Sequences > New sequence 2. Add 2+ email steps with subject/body/delay | Steps save in order with correct delays; canvas reflects them.
SEQ-002 | Builder | Recipients (List/Tag, Excluded, Advanced Filter) | 1. Configure included/excluded rows 2. Switch to Advanced Filter and build a condition | Recipient count updates correctly for both modes.
SEQ-003 | Builder | Global SMTP + send window + tracking | 1. Set SMTP once for the sequence 2. Set a step's send window/specific days 3. Enable tracking/UTM | All steps use the chosen SMTP; a step outside its window delays instead of sending; tracking data appears later in the report.
SEQ-004 | Run | Start now / Start scheduled | 1. Click Start Sequence 2. Try both 'now' and a future date/time | Contacts enroll and the first step sends immediately, or waits until the scheduled time.
SEQ-005 | Run | Pause / Resume / Reset & Re-run / Enroll new contacts | 1. Exercise each control from the topbar / Sequence Settings panel | Pause halts sends; Resume continues; Reset & Re-run restarts everyone; Enroll New only adds newly-matching contacts (no duplicates).
SEQ-006 | Run | Auto-complete & bounce handling | 1. Let a short sequence finish for all recipients 2. Include one undeliverable address | Status flips to Completed automatically; the bad address is recorded as Bounced and does not receive later steps.
SEQ-007 | Report | Email History & per-step drill-down | 1. Open View Report 2. Open a step's 'View Report' from its (...) menu | Email History shows sent/opens/clicks/status per step; drill-down filters Deliverability/Opens/Clicks/Unsubscribes/Bounced to that step only.
SEQ-008 | Diagnostics | Live queue & failed jobs | 1. Open 'View Live Status' while Active | Shows pending queued sends and any permanently-failed steps with a reason - nothing fails silently.

## Automation
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
AUTO-001 | Builder | Create automation with trigger + nodes | 1. Automation > Create 2. Set a trigger (e.g. tag applied) 3. Add Email / Wait / Condition / Webhook nodes | Flow saves; canvas shows nodes connected in order.
AUTO-002 | Run | Trigger fires the automation | 1. Perform the trigger action on a real contact (e.g. apply the watched tag) | Contact enters the automation and the first node executes (check contact journey).
AUTO-003 | Run | Contact journey view | 1. Open a specific contact's Journey for this automation | Shows each node the contact passed through with timestamps/outcomes.
AUTO-004 | Run | Condition branching | 1. Set up a condition node with a Yes/No branch 2. Trigger for contacts on each side | Each contact follows the correct branch based on the condition.
AUTO-005 | Webhook node | Test webhook node | 1. Add a Webhook node 2. Use 'Test Webhook' to fire a sample payload | Request is sent to the target URL and the result/response is shown.
AUTO-006 | Manage | Run/Restart/Report/Bulk delete | 1. Exercise Run, Restart, Report, and bulk delete from the Automation list | Each action behaves as labeled; Report shows aggregate stats for the automation.

## Sending & SMTP
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
SMTP-001 | SMTP Config | Add SMTP profile & test connection | 1. Sending > SMTP Config > Add 2. Fill host/port/credentials 3. Test Connection | Test reports success/failure clearly; valid profile saves.
SMTP-002 | SMTP Config | Set default sender | 1. Mark a profile as Default | New campaigns/sequences/etc. default to this profile when none is explicitly chosen.
SMTP-003 | OAuth | Connect Gmail / Microsoft via OAuth | 1. Add a profile using Google or Microsoft OAuth 2. Complete the consent flow | Connection succeeds and the profile can send a test email through the OAuth account.
SMTP-004 | OAuth | Expired/revoked token handling | 1. Revoke app access from the Google/Microsoft account 2. Try sending | A clear 'authorization invalid, re-authenticate' error is shown, not a silent failure.

## Webhooks
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
WHK-001 | Manage | Create inbound webhook | 1. Webhooks > Create 2. Copy the generated URL/secret | Webhook is listed as Active with a unique endpoint.
WHK-002 | Trigger | External POST creates/updates a contact | 1. Send a test POST to the webhook URL with contact fields | A contact is created or updated accordingly; entry appears in Webhook Logs.
WHK-003 | Manage | Regenerate secret / view logs / delete | 1. Regenerate the secret 2. Open Logs 3. Delete the webhook | Old secret stops working after regeneration; logs show recent deliveries; delete removes the webhook.

## Media, Settings & Global
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
GLB-001 | Media Library | Upload / browse / delete media | 1. Go to Media 2. Upload an image 3. Delete it | File appears in the library grid and is usable in the email editor; delete removes it.
GLB-002 | Settings | Update business settings & logo | 1. Settings > update business name/address 2. Upload a logo 3. Save | Changes persist and the logo reflects in the app header/emails where used.
GLB-003 | Notifications | Bell notifications | 1. Trigger an event that notifies (e.g. campaign completed) 2. Open the bell icon 3. Mark all read / clear | Notification appears, unread badge updates, and Mark all read / Clear behave as labeled.
GLB-004 | Search | Global search (Ctrl+K) | 1. Press Ctrl+K 2. Search for a contact/campaign/sequence by name | Relevant results appear and clicking one navigates to it.
GLB-005 | Navigation | Unimplemented nav stubs | 1. Click 'Templates' and 'Forms' in the sidebar | Flag current behavior (e.g. 404 or blank page) - these have no backend route yet as of this test pass.

## Cross-Cutting
ID | Feature Area | Test Case | Steps to Reproduce | Expected Result | Status | Notes / Bug Ref
XCUT-001 | Tracking | Open/click tracking pixel & links | 1. Send any campaign/sequence/recurring email with tracking on 2. Open it and click a link | Open and click are recorded and reflected in the relevant report within a few seconds.
XCUT-002 | Tracking | Unsubscribe link | 1. Click the unsubscribe link in a received email | Contact status becomes Unsubscribed; excluded from future sends across Campaigns/Sequences/Recurring/Automation.
XCUT-003 | Queue/Cron | Background sending keeps up | 1. Queue a send with many recipients 2. Confirm the cron-driven queue worker(s) are running | Emails drain steadily without the browser needing to stay open; no recipients get stuck 'queued' indefinitely.
XCUT-004 | Cross-tenant | Data isolation | 1. Log in as a second account 2. Check Contacts/Campaigns/Sequences | Only that account's own data is visible - no leakage between tenants.